## Cover
Contoso Financial Services (CFS) Module B Evidence Artifact — 4.2
Artifact | B4.2_DecisionLog_CFS_v1.xlsx
Control ID | 4.2
Control Name | Decision Log
Customer | Contoso Financial Services (CFS)
Industry | Regulated EU Fintech (PSD2 / DORA / GDPR)
Region | Sweden Central (swedencentral)
IaC stack | Bicep (primary) / Terraform AVM (alternate)
Prepared by | <<Partner Name>>
Reviewed by | <<Reviewer Name>>
Date | <<YYYY-MM-DD>>
Version | v1
Status | DRAFT — Complete highlighted cells
📋 INSTRUCTIONS: This template is pre-seeded with CFS context. Complete all cells highlighted in yellow. Do NOT modify column headers or control mappings. Save a copy as evidence-output/<filename> once complete.

## Decision Log
Architecture & Design Decision Log — Contoso Financial Services (CFS)
DL-ID | Date | Decision Area | Decision Made | Alternatives Considered | Decision Rationale | Impact (Cost/Risk/Schedule) | Owner | Approved By | Review Date | Status | Control Ref
DL-001 | 2025-01-15 | Network Topology | Adopt Hub & Spoke topology (ALZ Accelerator) with single hub in swedencentral | 1. Flat VNet (single VNet for all workloads) 2. Hub & Spoke 3. Virtual WAN (VWAN) | Hub & Spoke aligns with CAF/ALZ best practices, provides clear network segmentation, enables centralized security inspection via Firewall, and supports future expansion. VWAN deferred as overkill for initial lab scope. | Cost: Hub resources (FW, Bastion, GW) have baseline cost. Risk: Low — proven pattern. Schedule: No impact. | <<Partner Architect>> | <<CFS Arch Board>> | 2025-06-01 | Approved | B.2.1 B.4.2
DL-002 | 2025-01-15 | IaC Platform | Use Bicep (ALZ Accelerator) as primary IaC; Terraform AVM as alternate track | 1. Bicep only 2. Terraform only 3. ARM Templates 4. Pulumi | Bicep is Microsoft-native, has first-class Azure support, and aligns with ALZ Accelerator. Terraform AVM provides AVM parity and serves participants who prefer Terraform. ARM templates excluded (verbose). Pulumi excluded (requires licensed runtime in some cases). | Cost: None. Risk: Dual track adds maintenance overhead — mitigated by sharing modules. Schedule: +2 days for Terraform parity. | <<Partner Architect>> | <<CFS IT Manager>> | 2025-06-01 | Approved | B.2.1 B.4.2
DL-003 | 2025-01-15 | Firewall SKU | Deploy Azure Firewall Standard SKU (not Premium) for lab | 1. Azure Firewall Standard 2. Azure Firewall Premium 3. NVA (3rd party) | Standard SKU covers all lab scenarios (L4 network rules, L7 app rules, FQDN filtering). Premium adds TLS inspection and IDPS — valuable for production but increases lab cost by ~60%. NVAs excluded (require licenses). | Cost: ~€3/hour saving vs Premium. Risk: Missing IDPS testing — documented as known gap. Schedule: No impact. | <<Partner Architect>> | <<CFS CISO>> | 2025-06-01 | Approved | B.3.2 B.4.2
DL-004 | 2025-01-20 | Gateway Type | Use VPN Gateway (not ExpressRoute) for hybrid connectivity lab scenario | 1. VPN Gateway Site-to-Site 2. ExpressRoute + VPN failover 3. No hybrid connectivity | ExpressRoute requires physical circuit provisioning — not feasible in 1-day lab. VPN Gateway provides equivalent topology exercise and supports IKEv2 with BGP. ExpressRoute is documented as the production recommendation in design docs. | Cost: VPN GW ~€0.19/hour vs ER ~€0.40+/hour. Risk: VPN has higher latency than ER — documented. Schedule: No impact. | <<Partner Architect>> | <<CFS IT Manager>> | 2025-06-01 | Approved | B.3.2 B.4.2
DL-005 | 2025-01-22 | Private Endpoints | Enable Private Endpoints on all PaaS services (Key Vault, Storage, SQL) with private DNS zones | 1. Private Endpoints with private DNS 2. Service Endpoints (VNet Service Endpoints) 3. Public endpoints with IP firewall | Private Endpoints provide private IP routing — traffic never leaves VNet backbone. Service Endpoints don't provide private DNS and allow public endpoint to remain. IP firewall (option 3) is not Zero Trust compliant. PE + private DNS is the ALZ and CAF recommended pattern. | Cost: PE ~€0.01/hour per endpoint — negligible. Risk: DNS misconfiguration common — mitigated by automated Bicep deployment. Schedule: No impact. | <<Partner Architect>> | <<CFS CISO>> | 2025-06-01 | Approved | B.3.2 B.4.2
DL-006 | 2025-01-22 | Compute Access | Azure Bastion Standard SKU for VM access — no JumpBox VM, no public IPs | 1. Azure Bastion Standard 2. JumpBox VM with public IP 3. VPN + private RDP | Bastion provides browser-based RDP/SSH with no VM public IP — Zero Trust compliant. JumpBox requires hardening and patch management. VPN + private RDP is valid for production but adds complexity to lab. | Cost: Bastion Standard ~€0.19/hour. Risk: Low. Schedule: No impact. | <<Partner Architect>> | <<CFS IT Ops>> | 2025-06-01 | Approved | B.3.2 B.4.2
DL-007 | 2025-01-25 | Load Balancing (Internal) | Deploy Azure Internal Load Balancer (Standard SKU) for intra-spoke L4 load balancing | 1. Azure ILB Standard 2. Azure Application Gateway (internal mode) 3. DNS round-robin | ILB provides L4 TCP/UDP load balancing within the spoke. App Gateway provides L7 but adds cost duplication (App Gateway already deployed externally). DNS round-robin lacks health probing. ILB + App Gateway covers both L4 and L7 requirements. | Cost: ILB has no hourly charge (pay per rule). Risk: Low. Schedule: No impact. | <<Partner Architect>> | <<CFS AppDev>> | 2025-06-01 | Approved | B.3.2 B.4.2
DL-008 | 2025-01-25 | Global Delivery | Azure Front Door Standard (not Premium or CDN Classic) for global HTTP/S delivery | 1. AFD Standard 2. AFD Premium 3. Azure CDN Classic 4. Traffic Manager | AFD Standard provides global anycast, WAF, and health routing sufficient for lab. Premium adds Private Link origin (useful for production, adds cost). CDN Classic is being retired. Traffic Manager is DNS-only — no TLS termination or WAF. | Cost: AFD Standard ~€0.01/GB + fixed monthly. Risk: AFD Premium Private Link origin not demonstrated — documented gap. Schedule: No impact. | <<Partner Architect>> | <<CFS Arch Board>> | 2025-06-01 | Approved | B.3.2 B.4.2
DL-009 | 2025-01-28 | Log Analytics | Single central Log Analytics Workspace (cfs-hub-law-swc) — not per-workload | 1. Central LAW in hub (chosen) 2. Per-workload LAW 3. Azure Monitor Workspace only | Central LAW simplifies cross-resource correlation (SOC use case), aligns with ALZ monitoring baseline, and reduces cost vs multiple small workspaces. Per-workload adds complexity for no lab benefit. | Cost: LAW ingestion ~€2.30/GB. Risk: Central LAW becomes single point of failure for monitoring — mitigated by retention. Schedule: No impact. | <<Partner Architect>> | <<CFS SOC>> | 2025-06-01 | Approved | B.3.2 B.4.2
DL-010 | 2025-02-01 | DR / Multi-Region | Single region (swedencentral) for lab; DR documented as design-only | 1. Single region (chosen) 2. Active-active dual region 3. Active-passive with ASR | Multi-region deployment doubles cost and complexity — not feasible in 1-day lab. DR design (active-passive using ASR or AFD geo-routing) is documented in solution design as future state to satisfy B.2.1 auditor questions. | Cost: Avoids 2x resource cost. Risk: No DR tested — documented known gap. Schedule: No impact. | <<Partner Architect>> | <<CFS CISO>> | 2025-06-01 | Approved | B.2.1 B.4.2
DL-013
DL-014
DL-015
DL-016
DL-017